## Work units
Description | WBS
Project proposal | 1.1
Bibliographic review and theoretical documentation | 1.2.1; 1.3.1
Problem analysis and formal description | 1.2.2; 1.3.2
Project planning | 1.2.3;1.3.3
Proposed solution | 1.2.4;1.3.8
Analysis and design of the system | 1.2.5
System implementation | 1.2.6; 1.3.4-1.3.7;1.3.10
Parametric study | 1.3.9; 1.3.11
Experimental analysis | 1.2.7; 1.2.8; 1.3.12
Documentation and review | 1.2.9;1.4
Meetings | 1.5

## Basic costs
| Unit | Price/hour
Student | h | 15
Professor | h | 30

## Direct costs
Direct costs
Concept |  | Price/hour | Hours | Total price
Student | Project proposal | 15 | 3 | 45
| Bibliographic review and theorical documentation | 15 | 30 | 450
| Problem analysis and formal description | 15 | 24 | 360
| Project planning | 15 | 16.5 | 247.5
| Proposed solution | 15 | 24 | 360
| Analysis and design of the system | 15 | 9 | 135
| System implementation | 15 | 73.5 | 1102.5
| Parametric study | 15 | 25.5 | 382.5
| Experimental analysis | 15 | 40.5 | 607.5
| Documentation and review | 15 | 15 | 225
| Meetings | 15 | 25 | 375
| Total student |  | 286 | 4290
Professor | Project proposal | 30 | 3 | 90
| Meetings | 30 | 25 | 750
| Total professor |  | 28 | 840
Total |  |  |  | 5130

## Indirect costs
Indirect costs
Concept | Unitary cost | Unit type | Unities | Cost
Transport | 3.6 | daily | 13 | 46.8
GitHub Services | 7 | monthly | 6 | 42
License Microsoft Project Pro | 769 | unit | 1 | 769
License Microsoft Office Pro | 69 | unit | 1 | 69
Office consumables | 50 | monthly | 6 | 300
Computer | 22.9167 | monthly | 6 | 137.5
|  |  | Total | 1364.3

## Internal budget
Internal budget
Concept | Subtotal | Code | Percentage
Project proposal | 135 | CB1 | 2.632%
Bibliographic review and theorical documentation | 450 | CB2 | 8.772%
Problem analysis and formal description | 360 | CB2 | 7.018%
Project planning | 247.5 | CB1 | 4.825%
Proposed solution | 360 | CB3 | 7.018%
Analysis and design of the system | 135 | CB3 | 2.632%
System implementation | 1102.5 | CB4 | 21.49%
Parametric study | 382.5 | CB5 | 7.456%
Experimental analysis | 607.5 | CB5 | 11.84%
Documentation and review | 225 | CB6 | 4.386%
Meetings | 1125 | CB1/CB3 | 21.93%
Costs | 5130
Indirect costs (+30%) | 1773.59
Benefits (+30%) | 2071.077
Total | 8974.667

## Costumer budget
Code | Concept | Subtotal
CB1 | Project organization | 1653.2281
CB2 | Theoretical background | 1417.0527
CB3 | Design of the solution | 1850.041
CB4 | Implementation | 1928.7662
CB5 | Experimental analysis | 1731.9533
CB6 | Documentation | 393.6257
Total |  | 8974.667