## Planning
WBS | Task name | Time (days) | Time (hours) | Start | End | Predecessors WBS | Resources
1 | TFG | 118 | 286 | mon 22/01/18 | wed 04/07/18
1.1 | Project proposal | 1 | 3 | mon 22/01/18 | mon 22/01/18 |  | Student;Professor
1.2 | Documentation | 112 | 114 | wed 24/01/18 | mon 18/06/18 | 1.3[CC]
1.2.1 | Theoretical aspects | 10 | 15 | wed 24/01/18 | tue 06/02/18 | 1.3.1[CC] | Student
1.2.2 | Formal description of the problem | 8 | 12 | wed 07/02/18 | fri 16/02/18 | 1.2.1;1.3.1 | Student
1.2.3 | Project planning | 5 | 7.5 | tue 20/02/18 | mon 26/02/18 | 1.3.3[CC];1.2.2 | Student
1.2.4 | Proposed solution | 8 | 12 | tue 27/02/18 | thu 08/03/18 | 1.2.3 | Student
1.2.5 | Analysis and design of the system | 6 | 9 | fri 09/03/18 | fri 16/03/18 | 1.2.4 | Student
1.2.6 | Implementation documentation | 15 | 22.5 | wed 04/04/18 | tue 24/04/18 | 1.2.5;1.3.6 | Student
1.2.7 | Experimental analysis documentation | 15 | 22.5 | fri 11/05/18 | thu 31/05/18 | 1.2.6;1.3.11[FF] | Student
1.2.8 | Documentation of the conclusions | 5 | 7.5 | mon 04/06/18 | fri 08/06/18 | 1.3.12[CC];1.2.7 | Student
1.2.9 | Finish project report | 4 | 6 | wed 13/06/18 | mon 18/06/18 | 1.3;1.2.8 | Student
1.3 | Tasks | 108 | 144 | wed 24/01/18 | tue 12/06/18
1.3.1 | Bibliographic review | 10 | 15 | wed 24/01/18 | tue 06/02/18 | 1.1;1.5.1 | Student
1.3.2 | Problem analysis | 8 | 12 | thu 08/02/18 | mon 19/02/18 | 1.5.2 | Student
1.3.3 | Project plans definition | 6 | 9 | tue 20/02/18 | tue 27/02/18 | 1.3.2 | Student
1.3.4 | Initial prototype implementing split | 8 | 12 | thu 01/03/18 | mon 12/03/18 | 1.5.3 | Student
1.3.5 | Implementation and testing of operators | 7 | 10.5 | wed 14/03/18 | thu 22/03/18 | 1.5.4 | Student
1.3.6 | Implementation of parses and instances selection | 7 | 10.5 | mon 26/03/18 | tue 03/04/18 | 1.5.5 | Student
1.3.7 | Execution with different configurations and comparative with results to best so-far solutions | 6 | 9 | thu 05/04/18 | thu 12/04/18 | 1.5.6 | Student
1.3.8 | Modelling of uncertainty through tfns | 8 | 12 | mon 16/04/18 | wed 25/04/18 | 1.5.7 | Student
1.3.9 | Parametric study design and framework implementation | 7 | 10.5 | fri 27/04/18 | mon 07/05/18 | 1.5.8 | Student
1.3.10 | Improvement of the genetic operators | 6 | 9 | wed 09/05/18 | wed 16/05/18 | 1.5.9 | Student
1.3.11 | Parametric study | 10 | 15 | fri 18/05/18 | thu 31/05/18 | 1.5.10 | Student
1.3.12 | Result generation and conclusions | 7 | 10.5 | mon 04/06/18 | tue 12/06/18 | 1.5.11 | Student
1.4 | Review of the project report | 3 | 9 | tue 19/06/18 | thu 21/06/18 | 1.2 | Student
1.5 | Meetings | 116.5 | 24 | tue 23/01/18 | mon 02/07/18
1.5.1 | Meeting #1 | 1 | 2 | tue 23/01/18 | tue 23/01/18 | 1.1 | Professor;Student
1.5.2 | Meeting #2 | 1 | 2 | wed 07/02/18 | wed 07/02/18 | 1.5.1;1.3.1 | Professor;Student
1.5.3 | Meeting #3 | 1 | 2 | wed 28/02/18 | wed 28/02/18 | 1.3.3;1.5.2 | Professor;Student
1.5.4 | Meeting #4 | 1 | 2 | tue 13/03/18 | tue 13/03/18 | 1.3.4;1.5.3 | Professor;Student
1.5.5 | Meeting #5 | 1 | 2 | fri 23/03/18 | fri 23/03/18 | 1.3.5;1.5.4 | Professor;Student
1.5.6 | Meeting #6 | 1 | 2 | wed 04/04/18 | wed 04/04/18 | 1.3.6;1.5.5 | Professor;Student
1.5.7 | Meeting #7 | 1 | 2 | fri 13/04/18 | fri 13/04/18 | 1.3.7;1.5.6 | Professor;Student
1.5.8 | Meeting #8 | 1 | 2 | thu 26/04/18 | thu 26/04/18 | 1.3.8;1.5.7 | Professor;Student
1.5.9 | Meeting #9 | 1 | 2 | tue 08/05/18 | tue 08/05/18 | 1.3.9;1.5.8 | Professor;Student
1.5.10 | Meeting #10 | 1 | 2 | thu 17/05/18 | thu 17/05/18 | 1.3.10;1.5.9 | Professor;Student
1.5.11 | Meeting #11 | 1 | 2 | fri 01/06/18 | fri 01/06/18 | 1.3.11;1.5.10 | Professor;Student
1.5.12 | Meeting #12 | 0.5 | 2 | mon 02/07/18 | mon 02/07/18 | 1.3.12;1.5.11 | Professor;Student
1.6 | Defense request | 0.5 | 0.5 | tue 03/07/18 | wed 04/07/18 | 1.4;1.5.12 | Professor;Student
1.7 | Upload project report | 0.5 | 0.5 | tue 03/07/18 | wed 04/07/18 | 1.4;1.5.12 | Professor;Student